## Testcases
|  |  |  | Date | 2022-11-03
|  |  |  | Team ID | PNT2022TMID27747
|  |  |  | Project Name | News Tracker Application
|  |  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Pre-Requisite | Steps To Execute | Test Data | Expected Result | Actual Result | Status | Comments | TC for Automation(Y/N) | BUG ID | Executed By
LoginPage_TC_OO1 | Functional | Home Page | Verify user is able to see the Login/Signup page when user land on the page |  | 1.Enter URL and click go 2.Verify login/Singup page displayed or not |  | Login/Signup page should display | Working as expected | Pass |  | N
LoginPage_TC_OO2 | UI | Login page | Verify the UI elements in Login/Signup page |  | 1.Enter URL and click go 3.Verify login/Singup page with below UI elements: a.email text box b.password text box c.Login button d.New customer? SignUp button e.News topics buttons |  | Application should show below UI elements: a.email text box b.password text box c.Login button d.New customer? Sign UP button. e.Favourite topics card in signup section. | Working as expected | Pass |  | N
LoginPage_TC_OO3 | Functional | Login page | Verify user is able to log into application with Valid credentials |  | 1.Enter URL and click go 2.Enter the credentials in the text box. 3.If the user is verified you will be redirected to the home page. | Username: test@gmail.com password: Testing123 | User should be redirected towards the home page. | Working as expected | Pass |  | N
HomePage_TC_001 | Fuctional | Home page | verify the user is able to see the home page. |  | 1. Login and go to the site |  | Application should show the news | Working as expected | Pass |  | N
HomePage_TC_002 | Functional | Home page | Verify user is able to view news under specific categories |  | 1. Go to the site 2. Click on topics button |  | Application should show news releated to that topic | Working as expected | Pass |  | N
HomePage_TC_003 | Functional | Home page | Verify user is able to view recommended news |  | 1. Go to the site 2. Click on recommended tab |  | Application should show the news based on user's interest | Working as expected | Pass |  | N
HomePage_TC_004 | Functional | Home page | Verify user is able to bookmark a product |  | 1. Go to the site 2. Click on bookmark icon in the news card. |  | Application should show saving icon and the news is bookmarked | Working as expected | Pass |  | N
HomePage_TC_005 | Functional | Home page | Verify user is able to navigate to the news article page |  | 1. Go to the site 2. Click on any news card |  | Application should navigate to the article page where the actual article is displayed. | Working as expected | Pass |  | N
BookmarkPage_TC_001 | Functional | Bookmark page | Verify user is able to view the bookamarks |  | 1. Go to the site 2. Click on bookmarks tab under the user icon |  | Application should view all the user bookmarks | Working as expected | Pass |  | N
BookmarkPage_TC_002 | Functional | Bookmark page | Verify the user whether they can delete a bookmark |  | 1. Go to the bookamarks page. 2. Click on the bookmark icon in the page |  | Application should show the deleting icon and the bookmark should be deleted. | Working as expected | Pass |  | N
NewsPage_TC_001 | Functional | News page | Verify user is able to view the news |  | 1. Go to the site 2. Click on a news card |  | Application should show the news article | Working as expected | Pass |  | N
NewsPage_TC_002 | Functional | News page | Verify user is able to view page not loading text |  | 1. Go to the site 2. Click on a news card |  | Application should show page not loading text | Working as expected | Pass |  | N
NewsPage_TC_003 | Functional | News page | Verify user is able to view the news article by click on page not loading text |  | 1. Go to the site 2. Click on a news card 3. Click on page not loading text. |  | Applicatoin should redirect to the actual article page | Working as expected | Pass |  | N
Logout_TC_001 | Functional | Logout Logic | Verify user is able to logout of the application |  | 1. Go to the site 2. Click on user icon 3. Click on logout |  | Application should logout the user. | Working as expected | Pass |  | N